## Schedule
Database Migration DB2 --> Sql Server
Year |  | : 2024
Rev |  | : 00
No | Online Application Name | Departement | Made by | Item Menu Modified | PIC Modified | Month | 2024-07-01 |  |  |  |  | 2024-08-01 |  |  |  |  | 2024-09-01
[6 empty] | Week | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
1 | brs-stock | Brushing | hadi |  |  | Plan
Act
2 | brushing-new | Brushing | deden |  |  | Plan
Act
3 | dye-itti | Dying | ilham | 38 | Ilham | Plan
Act
4 | finishing2-new | Finishing | deden |  |  | Plan
Act
5 | fin-itti-new | Finishing | deden |  |  | Plan
Act
6 | laborat | Laborat | ilham |  |  | Plan
Act
7 | laporan | All | nilo |  |  | Plan
Act
8 | mkt-itti | Marketing | tobi | 40 | Tobi | Plan
Act
9 | NOWgdb | Gudang Gray | usman |  |  | Plan
Act
10 | NOWgerobak | Gudang Gray | usman |  |  | Plan
Act
11 | NOWgkg | Gudang Gray | deden |  |  | Plan
Act
12 | NOWgkgLaporan | Gudang Gray | deden |  |  | Plan
Act
13 | NOWgkj | Gudang Kain Jadi | usman |  |  | Plan
Act
14 | NOWknt | Knitting | usman |  |  | Plan
Act
15 | NOWmkt | Marketing | usman |  |  | Plan
Act
16 | NOWmtc | Maintenance | usman |  |  | Plan
Act
17 | NOWqcf | QC Final | usman |  |  | Plan
Act
18 | QC After Sales | QC | hadi | 19 | Hadi | Plan
Act
19 | qc-stock | QC | hadi |  |  | Plan
Act
34/38
18/40
15/19

## Application Support (Buy)
Syncronize tools :
Cdata Syncronize estimasi cost lisence : 5000 $ / yr

## QC
Schedule migrasi after sales
date | : 2024-07-31
NO | Menu Application | Item Modify | Month | Juni | July |  |  |  |  | Agustus
|  |  | Week | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W5
1 | Report KPE | 6 | Plan
Act
2 | Report Ganti Kain | 2 | Plan
Act
3 | Report Retur | 1 | Plan
Act
4 | Report TPU KPE | 2 | Plan
Act
5 | Report Disposisi | 3 | Plan
Act
6 | Report Now | 3 | Plan
Act
7 | Bon Penghubung | 2 | Plan
Act
8 | Syncronisasi | 2 | Plan
| Online dan Migrasi |  | Act
Start Evaluasi